## Sheet1
BASIC RISK ASSESSMENT TEMPLATE
ID NO. | RISK or HAZARD DESCRIPTION | RESOURCES IMPACTED e.g., personnel, machinery | EXISTING CONTROL MEASURES | PROBABILITY LEVEL | IMPACT LEVEL | PREVENTION MEASURES | ASSIGNED TO | START DATE | DUE DATE | STATUS | LEVEL KEY | STATUS KEY
1 | Absence of a formal cybersecurity program, documented policies, Governance, Risk, and Compliance (GRC) functions, and a formal risk management process. | Personnel (security team, executives), Information Systems, Organizational Processes | - Informal security practices - Ad-hoc risk-related activities like patching | High | High | - Develop and implement a formal cybersecurity framework (e.g., NIST, ISO 27001) - Establish a dedicated GRC team - Document and formalize risk management processes - Regular training and awareness programs for staff - Conduct periodic security assessments and audits | Jonathan Jobs, CISO; Security Program Team | 2024-11-01 | 2025-05-01 | Not Started | High | Not Started
2 | Vulnerabilities in AI models, including AI poisoning, attack vectors on AI, model deviations, and shadow AI, affecting disaster prediction and claims processing. | AI Models, Data Scientists, IT Infrastructure, Customer Trust | - AI models secured with disclaimers - Microsegmentation and higher controls on sensitive data - Routine data cleaning | Medium | High | - Implement AI-specific security measures (e.g., model integrity checks, anomaly detection) - Restrict access to AI models and training data - Continuously monitor AI model behavior for deviations - Conduct regular AI security audits and vulnerability assessments - Establish policies for shadow AI | AI Security Team; Jonathan Jobs, CISO | 2024-11-01 | 2025-05-01 | Not Started | Medium | In Progress
3 | Lack of formal compliance processes and regular audits despite awareness of compliance needs across regions and existing liability insurance. | Compliance Team, Legal Department, All Departments Handling Data, IT Systems | - Awareness of compliance requirements - Existing cybersecurity liability insurance | Medium | High | - Develop and implement formal compliance processes - Conduct regular compliance audits - Hire or assign compliance officers - Implement automated compliance monitoring tools - Stay updated with regional regulations and adjust policies accordingly | Rhea Ripley, CIO; Compliance Team | 2024-11-01 | 2025-05-01 | Not Started | Low | Complete
4 | Outsourced functions lack contracts to protect data and there are no formal third-party risk management processes in place. | Third-Party Vendors, Procurement Team, Legal Department, IT Systems | Some functions outsourced | High | High | - Develop and implement formal third-party risk management processes - Include data protection clauses in all third-party contracts - Conduct regular security assessments of third-party vendors - Monitor third-party compliance with security standards - Use third-party risk management tools | Procurement Team; Rhea Ripley, CIO |  | 2025-05-01 | In Progress | Low | Complete
5 | Existing Single Sign-On (SSO) and Multi-Factor Authentication (MFA) are in place, but there is a need for a comprehensive IAM strategy, including role-based access controls and regular access reviews, especially with multi-cloud expansion. | IT Systems, Personnel Access, Data Security | SSO and MFA implemented | Medium | High | - Develop a comprehensive IAM strategy - Implement Identity Governance and Administration (IGA) solutions - Establish role-based access controls (RBAC) - Conduct regular access reviews and audits - Automate access management processes where possible | IT Security Team; Jonathan Jobs, CISO | 2024-11-01 | 2025-05-01 | Not Started |  | Overdue
6 | No formal cybersecurity training programs are in place, and building a strong security culture is still a future focus rather than a current reality. | All Employees, HR Department, Training Resources | Initial focus on integrating security into app redevelopment | High | Medium | - Develop and implement comprehensive, ongoing cybersecurity training programs - Conduct regular phishing simulations and awareness campaigns - Identify and train security champions within teams - Regularly communicate security policies and updates to all employees | HR Department; Jonathan Jobs, CISO |  | 2025-05-01 | In Progress |  | On Hold
7 | Basic business continuity measures are in place via AWS contracts and US data centers, but there are no formal backup and disaster recovery (DR) plans or a dedicated business continuity team. | IT Systems, Data Centers, Business Operations, Personnel | - Basic BC measures via AWS contracts - Data centers located in the US | Medium | High | - Develop and implement comprehensive BC and DR plans - Establish a dedicated business continuity team - Conduct regular BC/DR drills and simulations - Implement robust backup solutions with offsite and geographically dispersed storage - Define clear recovery time objectives (RTO) and recovery point objectives (RPO) | Operations Team; Rhea Ripley, CIO | 2024-11-01 | 2025-05-01 | Not Started
8 | Data obfuscation techniques in testing environments are not fully formalized, and there is a need to enhance data protection strategies to safeguard sensitive information. | Data Storage Systems, Development Teams, IT Security | - Data classification in place - Microsegmentation and higher controls on sensitive data | Medium | Medium | - Formalize data obfuscation and anonymization processes in testing environments - Implement advanced encryption for sensitive data at rest and in transit - Conduct regular data protection audits - Enhance data governance policies to include data minimization and secure data lifecycle management | Data Protection Officer; IT Security Team |  | 2025-05-01 | In Progress
9 | Assets are distributed across cloud and on-premises environments without a centralized inventory, leading to incomplete asset management and the need for continuous monitoring. | IT Infrastructure, Cloud Services, On-Premises Systems, Security Team | Assets are distributed across AWS, on-premises, and SaaS environments | High | Medium | - Develop a centralized asset inventory system - Implement asset management tools for continuous monitoring - Conduct regular asset audits and reconciliations - Define asset ownership and classification standards - Integrate asset management with the overall security framework | IT Operations Team; Jonathan Jobs, CISO |  | 2025-05-01 | In Progress
10 | Employees use personal devices (BYOD) without a Mobile Device Management (MDM) solution, and some team members work remotely, increasing the risk of malware infections, data leakage, and unauthorized access. | Personal Devices, Remote Work Infrastructure, IT Security, All Employees | Single Sign-On (SSO) and Multi-Factor Authentication (MFA) for applications | High | Medium | - Implement a Mobile Device Management (MDM) solution - Define and enforce BYOD policies - Provide secure VPN access for remote workers - Enforce security controls on personal devices (e.g., antivirus, encryption) - Conduct regular security assessments for remote work setups | IT Security Team; Jonathan Jobs, CISO | 2024-11-01 | 2025-05-01 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET